## Hours
Hightett Common Building F - Duplex |  | Total Allowed Hours 193 =
| Allowance | Actual
0. Dismantling | 0
1. Induction, ACW, shaft site walk, delivery | 8
2. Installing of hoisting equipment and test hitch point | 4
3. Plumbing and hoistway survey | 3
4. Installing mech pit components, buffers, trimmers | 6
5. 1st set rails (first 2 rings) | 4
6. CW tank, fill with required weight | 4
7. All other rails in shaft, bow in | 4
8. Building Car structure as working platform | 4
9. INEX OST, INEX Install & Sign off | 4
10. 2nd Rail (5m) Brackets and guide rails | 4
11. 3rd Rail (5m) Brackets and guide rails | 4
12. 4th Rail (5m) Brackets and guide rails | 4
16. 5th Rail (5m) Brackets and guide rails | 4
14. 6th Rail (5m) Brackets and guide rails | 0
16. 7th Rail (5m) Brackets and guide rails | 0
16. 8th Rail (5m) Brackets and guide rails | 0
17. 9th Rail (5m) Brackets and guide rails | 0
18. Cut top rails, fit bed plate | 5
19. Governor | 3
20. Install Motor | 4
21. Top door frame/controller frame | 4
22. Motor spin Fitter - Prepare doors | 3
23. Motor spin Fitter - Prepare door frames | 3
24. Motor spin Fitter - Prepare interior | 2
25. Motor spin Elec - wires headroom - minimum to spin | 6
26. Motor spin Elec - wires controller | 2
27. Motor Spin Elec - Motor spinning | 0
28. Belt Lift Fitter - 2 Installers | 8
29. Belt Lift Elec - 2 Installers | 8
30. 1st Door Frame assembly installation | 4
31. 2nd Door Frame assembly installation | 4
32. 3rd Door Frame assembly installation | 4
33. 4th Door Frame assembly installation | 4
34. 5th Door Frame assembly installation | 4
35. 6th Door Frame assembly installation | 4
36. 7th Door Frame assembly installation | 4
37. 8th Door Frame assembly installation | 4
38. 9th Door Frame assembly installation | 0
39. 10th Door Frame assembly installation | 0
40. 11th Door Frame assembly installation | 0
41. 12th Door Frame assembly installation | 0
42. Install front of Car door assembly | 4
43. Install factory Interior | 2
44. Install factory Interior Second Person | 2
45. Hoistway wiring (1hr per floor) | 9
46. Pit Wiring | 4
47. Headroom wiring | 4
48. Car Wiring | 4
49. Buttons and Indicators wiring | 8
50. Security wiring | 10
51. Final tasks before commissioning (clean-up/rubbish removal) | 0
52. Commissioning Lift | 8
53. Tune Doors | 8
54. SAIS Testing Tester | 8
55. SAIS Testing Tuner | 8
60. Other Productive hours (VO, etc) | 0
61. Other Non-Productive hours (site readiness, etc) | 0
62. Builders Lift Re-tune + Test | 0